## Overview
STREET LEGENDS: 30-DAY ACTION PLAN TRACKER
Phase 0: Assess/Pre-Event ¦ February 1 - March 1, 2026
MISSION
Secure all foundational event and stakeholder contracts to green-light the Street Legends travel docu-series for production.
WEEKLY OBJECTIVES
Week 1 (Feb 1-7) | Stakeholder Alignment & Onboarding
Import contacts to Align, send Reality Check messages, schedule discovery calls
Week 2 (Feb 8-14) | Contract Distribution & Negotiation
Distribute contracts, negotiate terms, define Super Circus operations
Week 3 (Feb 15-21) | Finalize Agreements & Secure Commitments
Finalize contracts, secure commitments, create Right of Use agreements
Week 4 (Feb 22-28) | Execute Contracts & Prepare for State Funding
Obtain signatures, collect capital, prepare state funding requests
KEY STAKEHOLDER CATEGORIES
• NHRA Events - Venue contracts, filming permissions, event dates
• NASCAR Events - Venue contracts, filming permissions, event dates
• Super Circus - Master service agreement (state-by-state operations)
• Auto Industry Sponsors - Contribution agreements, branding rights
• Event Crew - Service agreements for live event execution
• Z Crew (Content Capture) - Production service agreements
• Venues - Filming permissions, access agreements, insurance
SUCCESS CRITERIA (March 1 Deadline)
✓ All 50+ stakeholders onboarded to Align platform
✓ Master Alignment Agreement (MAA) executed with all key parties
✓ Super Circus state-by-state operations defined and contracted
✓ All venue contracts signed with filming permissions
✓ Event Crew and Z Crew service agreements executed
✓ Sponsor contribution agreements signed with Right of Use
✓ Initial capital contributions collected
✓ State/local funding requests prepared and submitted
✓ Project GREEN-LIT for production planning
NAVIGATION
→ Week 1 (Feb 1-7)
→ Week 2 (Feb 8-14)
→ Week 3 (Feb 15-21)
→ Week 4 (Feb 22-28)
→ Stakeholder Database
→ Contract Status
Generated: February 04, 2026

## Week 1 (Feb 1-7)
WEEK 1: Stakeholder Alignment & Onboarding
February 1-7, 2026
Task | Owner | Due Date | Status | Notes
Import all 50+ contacts to Align platform | Brandy | Feb 2 | Not Started | Create 'Street Legends' room
Tag contacts with provisional roles | Brandy | Feb 2 | Not Started | Sponsor/Venue/Service Provider
Send Reality Check message to all stakeholders | Brandy | Feb 3 | Not Started | Use template from docs
Schedule discovery call: Super Circus | Brandy | Feb 4 | Not Started | Priority #1
Schedule discovery call: NHRA venues | Brandy | Feb 4 | Not Started | Priority #2
Schedule discovery call: NASCAR venues | Brandy | Feb 4 | Not Started | Priority #3
Schedule discovery call: Auto Industry sponsors | Brandy | Feb 5 | Not Started | Identify top 5
Prepare contract templates for review | Brandy | Feb 6 | Not Started | 5 templates ready
Create Jimmy McNickle private Align room | Brandy | Feb 2 | Not Started | Separate from main project
Hold initial evaluation meetings (top 10) | Brandy | Feb 5-7 | Not Started | Determine pathways
← Back to Overview

## Week 2 (Feb 8-14)
WEEK 2: Contract Distribution & Negotiation
February 8-14, 2026
Task | Owner | Due Date | Status | Notes
Distribute Venue Agreement to NHRA contacts | Brandy | Feb 8 | Not Started | Include filming permissions
Distribute Venue Agreement to NASCAR contacts | Brandy | Feb 8 | Not Started | Include filming permissions
Distribute Super Circus Master Service Agreement | Brandy | Feb 9 | Not Started | State-by-state operations
Negotiate Super Circus load-in/load-out terms | Brandy | Feb 10 | Not Started | Critical for logistics
Distribute Sponsor/Contributor Agreements | Brandy | Feb 11 | Not Started | Right of Use included
Distribute Event Crew Service Agreements | Brandy | Feb 12 | Not Started | Define scope of work
Distribute Z Crew Service Agreements | Brandy | Feb 12 | Not Started | Content capture specs
Negotiate sponsor branding rights | Brandy | Feb 13 | Not Started | Logo placement, credits
Define Super Circus concession operations | Brandy | Feb 14 | Not Started | Revenue sharing model
Review all contract feedback | Brandy | Feb 14 | Not Started | Prepare for Week 3 finalization
← Back to Overview

## Week 3 (Feb 15-21)
WEEK 3: Finalize Agreements & Secure Commitments
February 15-21, 2026
Task | Owner | Due Date | Status | Notes
Finalize all contract terms | Brandy | Feb 17 | Not Started | All parties aligned
Secure verbal commitments from all stakeholders | Brandy | Feb 17 | Not Started | Document in Align
Create Right of Use Agreements for contributors | Brandy | Feb 18 | Not Started | Link funds to project
Lock down filming permissions with all venues | Brandy | Feb 18 | Not Started | Z Crew access confirmed
Finalize Super Circus state-by-state operations | Brandy | Feb 19 | Not Started | All states defined
Confirm Event Crew availability and rates | Brandy | Feb 19 | Not Started | Lock in team
Confirm Z Crew availability and rates | Brandy | Feb 20 | Not Started | Lock in team
Prepare Master Alignment Agreement (MAA) | Brandy | Feb 21 | Not Started | Incorporate all sub-agreements
Review all insurance requirements | Brandy | Feb 21 | Not Started | Venues, crews, events
Prepare Week 4 signature packets | Brandy | Feb 21 | Not Started | Ready for execution
← Back to Overview

## Week 4 (Feb 22-28)
WEEK 4: Execute Contracts & Prepare for State Funding
February 22-28, 2026
Task | Owner | Due Date | Status | Notes
Obtain signatures on all venue contracts | Brandy | Feb 24 | Not Started | Digital via Align/Beneflts
Obtain signatures on Super Circus agreement | Brandy | Feb 24 | Not Started | Master service agreement
Obtain signatures on Event Crew agreements | Brandy | Feb 25 | Not Started | All crew members
Obtain signatures on Z Crew agreements | Brandy | Feb 25 | Not Started | All production crew
Obtain signatures on Sponsor agreements | Brandy | Feb 26 | Not Started | All contributors
Collect initial capital contributions | Brandy | Feb 26 | Not Started | Per payment schedules
Execute Master Alignment Agreement (MAA) | Brandy | Feb 27 | Not Started | All parties sign
Package contracts for state funding requests | Brandy | Feb 27 | Not Started | Economic dev, tourism
Submit state/local funding requests | Brandy | Feb 28 | Not Started | All applicable states
PROJECT GREEN-LIT: Begin production planning | Brandy | Mar 1 | Not Started | Enter Phase 1: Assess/Pre-GRID
← Back to Overview

## Stakeholder Database
STAKEHOLDER DATABASE
Track all 50+ Street Legends stakeholders
Name | Organization | Category | Role | Contact | Align Status | Priority | Notes
|  | NHRA | Venue Contact |  | Not Invited | High
|  | NASCAR | Venue Contact |  | Not Invited | High
|  | Super Circus | Service Provider |  | Not Invited | Critical | Master agreement required
|  | Auto Industry | Sponsor |  | Not Invited | High
|  | Event Crew | Service Provider |  | Not Invited | Medium
|  | Z Crew | Production |  | Not Invited | Medium | Content capture
← Back to Overview

## Contract Status
CONTRACT STATUS TRACKER
Track all contract executions for Master Alignment Agreement
Stakeholder | Contract Type | Sent Date | Reviewed | Negotiated | Signed Date | Status | Notes
| Venue Agreement |  | No | No |  | Not Started | NHRA venue
| Venue Agreement |  | No | No |  | Not Started | NASCAR venue
| Super Circus Master |  | No | No |  | Not Started | State-by-state ops
| Sponsor Agreement |  | No | No |  | Not Started | Right of Use
| Event Crew Service |  | No | No |  | Not Started
| Z Crew Service |  | No | No |  | Not Started | Content capture
← Back to Overview